## DIS WBS

Hypothetical WBS assuming that the project will last for 10 years, as indicated by the brief.

* 1.0 Initiating
  + 1.1 Select project manager
  + 1.2 Form project team
  + 1.3 Feasibility study
  + 1.4 Develop project charter
* 2.0 Planning
  + 2.1 Scope
    - 2.1.1 Plan scope management
    - 2.1.2 Gather requirements
      * 2.1.2.1 Cultural requirements
      * 2.1.2.2 Technical requirements
    - 2.1.3 Define scope
    - 2.1.4 Define assumptions
    - 2.1.5 Create WBS / WBS dictionary
    - 2.1.6 Validate scope
  + 2.2 Time
    - 2.2.1 Plan schedule management
    - 2.2.2 Define activities
    - 2.2.3 Sequence activities
    - 2.2.4 Estimates
      * 2.2.4.1 Activity resources
      * 2.2.4.2 Activity durations
    - 2.2.6 Develop schedule
  + 2.3 Cost
    - 2.3.1 Plan cost management
    - 2.3.2 Estimate costs
    - 2.3.3 Determine budget
  + 2.4 Quality
    - 2.4.1 Plan quality management
  + 2.5 Human resources
    - 2.5.1 Plan human resources management
    - 2.6.1 Acquire project team
  + 2.6 Communications
    - 2.6.1 Plan communications management
  + 2.7 Risk
    - 2.7.1 Plan risk management
    - 2.7.2 Identify risks
    - 2.7.3 Risk analysis
      * 2.7.3.1 Qualitative risk analysis
      * 2.7.3.2 Quantitative risk analysis
    - 2.7.4 Plan risk responses
  + 2.8 Procurement
    - 2.8.1 Plan procurement management
  + 2.9 Stakeholders
    - 2.9.1 Identify stakeholders
    - 2.9.2 Plan stakeholder management
* 3.0 Executing
  + 3.1 Tablet
    - 3.1.1 Procure tablets
    - 3.1.2 Distribute tablets
  + 3.2 Wireless internet
    - 3.2.1 Procure infrastructure
    - 3.2.2 Install infrastructure
  + 3.3 Applications
    - 3.3.1 Develop applications
    - 3.3.3 Deploy applications to tablet
  + 3.4 Testing
    - 3.4.1 Test sample subset of tablets
    - 3.4.2 Test wireless infrastructure
      * 3.4.2.1 Pre installation
      * 3.4.2.2 Post installation
    - 3.4.3 Test applications
      * 3.4.3.1 Pre deployment
      * 3.4.3.2 Post deployment
  + 3.5 Support
    - 3.5.1 Develop support for tablets
    - 3.5.2 Develop support for wifi
    - 3.5.2 Develop support for applications
  + 3.6 Stakeholders
    - 3.6.1 Manage stakeholder engagement
    - 3.6.2 Control stakeholder engagement
* 4.0 Monitoring and controlling
  + 4.1 Project management control
    - 4.1.1 Control scope
    - 4.1.2 Control schedule
    - 4.1.3 Control costs
    - 4.1.4 Quality
      * 4.1.4.1 Control quality
      * 4.1.4.2 Quality assurance
    - 4.1.5 Control communications
    - 4.1.6 Control risk
    - 4.1.7 Control procurements
  + 4.2 User engagement
    - 4.2.1 Monitor via social media
* 5.0 Closing
  + 5.1 Deliver products
  + 5.2 Close procurements
  + 5.3 Update process assets

## Team WBS

Will add this to the Project 2013 file as well, so we can track how we are doing. Based on stages:

* Stage 1
  + Prelim scope table
  + Out of scope table
  + WBS / WBS dictionary
  + Stage 1 progress report
* Stage 2
  + Stakeholder analysis table
  + HR requirements table
  + Risk assessment table
  + Stage 2 progress report
* Stage 3
  + Communications strategy table
  + Quality strategy
  + Procurement strategy
  + Stage 3 progress report
* Stage 4
  + Project cost breakdown table
  + Gantt chart
    - Milestones
    - Deliverables
  + Stage 4 progress report
* Final
  + Submit proposal